## Slide 1
Fail to plan. Plan to fail.

## Slide 2
County Judge – Bee County, Texas
Honorable Stephanie Moreno
Fiscal Conservative
Respectful of taxpayer dollars and the impact her decisions have on property owners
Diligent
Does her homework and asks tough questions.
Passionate
Loves her job and is grateful for the opportunity to serve her community.
Honest
Tell it like it is.

## Slide 3
Senior Vice President, ECM International, Inc.
Brenda Jenkins
Advocate
Protect the Owner – No Exceptions
Leader
Servant Leader = Communication, Trust, and Respect.
Accomplished
1st Woman Executive Director at Public Utility Commission of Texas
Process Geek
I have a plan for that.

## Slide 4
Hazardous Conditions Ahead
Planning & Execution
Project Concept
Starts with design?
Design
Construction

## Slide 5
Stages of a Project
Piece by Piece what to look for.
Success vs. Failure
A few examples
Why?!
The Best Examples
How?!
Step by Step Plan

## Slide 6
Beach front property in Arizona
What you want to hear
Initiation of the project
Procurement
Scope
Finance
Procurement -2nd Phase
Construction
Input from Internal Stakeholders
Verify the Need
Identify the Budget
Court Approval to Start Process
Issue RFQ for the Design Team
Negotiate Contract
Select the Site
Surveys
Meetings with Staff, Constituents
Begin Programming
Review the Conceptual Design
Cost Estimate of Conceptual Design
Input from Internal Stakeholders
Verify the Need
Identify the Budget
Court Approval to Start Process
Hire the Contractor
Negotiate Price
Value Engineering
Hire geotechnical, FFE, IT, AV, Commissioning, Testing
Permits
Site Inspections
Budget
Invoice Approval
Quality Control
Change Order Management
Schedule

## Slide 7
PROJECT DEVELOPMENT PHASE
The planning phase of a project
Getting to the Starting Line
Project Concept to Funding
Interdependent and Simultaneous Activities
Greatest Influence on Success of a Project

## Slide 8
Planning lets you impose order on the chaotic process of making something new.

## Slide 9
Where all ROADS converge. Enter at your own RISK
The Spaghetti Bowl
Project Concept
C.O.
Total Project Cost
Public Involvement
Committees
Implementation Strategy
Financing
G.O.
Resources
Procurement
Project Controls
Financial Advisor
Soft Costs
Scheduling
Delivery Method
Site Selection
Master Schedule
Bond Committee
Public Input
Public
Education

## Slide 10
Project Development CRITICAL Components
Categories of Project Development
Project Concept
Financing
Total Project Cost
Public Involvement
Committees
Implementation Strategy
Master Schedule

## Slide 11
The Beginning and The End
Project Concept
Defining the Project Concept is at the epicenter of the Project Development Phase. All other tasks and activities in the Project Development impact the Project Concept. The product of the Project Development is a Project that you can afford, can fund, has a reliable cost estimate, where public involvement and participation is incorporated, where internal processes and controls are mapped, procurement and resources are assembled into a successful Implementation Strategy.
Defining the Project
Needs Assessment
Facilities Assessment

## Slide 12
A plan without funding is just a wish.
Financing
Bond Counsel
Financial Advisor
Certificate of Obligation
General Obligation
Prepares Bond Order and shepherds through Attorney General’s review process, provide opinions to the bond’s validity.
Guides the economic side of the process. Structure the Transaction and arranges the sale of bonds. Assist in obtaining rates, insurance, securing banking arrangements to complete the transaction
One of several types of funding mechanisms. Does not require an election. Does require court approval and public posting to allow citizens to petition for a Bond Election.
Used often. Bond election required with voter approval to proceed with a project.
B
F
C
G

## Slide 13
Capture ALL costs
Total Project Cost
Can exceed 30% of the cost of a project beyond the cost of work
Owners responsibility for contracts, services, and equipment beyond the Designer and Builder contracts
Cost of land and financing costs
Account for up-front costs and county-performed work
Project Budget Review

## Slide 14
Project Delivery Methods
Managing Risk
DESIGN-BID-BUILD
COMPETETIVE
SEALED PROPOSAL
CONSTRUCTION
MANAGER AT RISK
The traditional U.S. project delivery method typically involves three sequential project phases: This sequence usually leads to a sealed bid, fixed-price contract.
A Request for Proposals (RFP) is the solicitation document for this method of procurement. It is used when price and qualifications are critical factors
Commitment in the Design Phase to fill in gaps, provide real-time pricing. Provide a Guaranteed Maximum Price (GMP)before design is complete
One contract for the Owner. Contractor holds the contract with the Architect. Design and construction cost are simultaneous. Provide a GMP before design is complete.
A contractual arrangement where the CMA is the Owner’s Representative and the Contractor is a Prime and the Owner holds contracts with subcontractors directly. Variations exist on the structure
Highest Risk
Lowest Risk
Varies
DESIGN-BUILD
CONSTRUCTION
MANAGER AS
AGENT

## Slide 15
Project Delivery Methods
Managing Risk
DESIGN-BID-BUILD
COMPETITIVE
SEALED PROPOSAL
CONSTRUCTION
MANAGER AT RISK
ADVANTAGES:
Familiar
Easy Accounting
One Contract w/ Designer
One Contract w/Builder
DISADVANTAGES:
Familiar
Easy Accounting
One Contract w/ Designer
One Contract w/Builder
ADVANTAGES:
Same as DBB except adds flexibility for Qualifications-based selection
DISADVANTAGES:
Familiar
Easy Accounting
One Contract w/ Designer
One Contract w/Builder
ADVANTAGES:
One contract w/Designer and one w/ Builder
CMR participates in Design Phase
Expedited Schedule
Guaranteed Maximum Price
Transparency
Transfers Risk from Owner
DISADVANTAGES:
Unfamiliarity leads to major management mistakes
Difficult Accounting
ADVANTAGES:
Shares advantages of CMR
One contract
Eliminates adverse relationship
DISADVANTAGES:
Unfamiliarity leads to major management mistakes
Market Driven
One contract
ADVANTAGES:
Serves as Advisor
DISADVANTAGES:
May be used incorrectly
May increase staff requirements of the Owner
Involves greater risk to the owner without the required elements
DESIGN-BUILD
CONSTRUCTION
MANAGER AS
AGENT

## Slide 16
Site Selection
Turn around, don’t drown.
Most precarious component of a project. Involves a mix of public debate along with technical and financial considerations. Tangible and Intangible considerations and often high visibility.
SITE CONDITIONS
Frequent source of dispute between designers, contractors, and owners.
AFFECTED
Operations, cost, and appearance of the new facility
CONSIDER
Public Interest, Technical, and Financial
Lessons Learned Can be the most unknown & volatile element of TPC.
LESSONS

## Slide 17
Managing The Schedule = Managing the Cost
Master Schedule
Creating the Master Schedule must consider ALL other elements. Financing with G.O has mandated schedules. Procurement has mandated timelines for posting and preliminary schedules should be part of the procurement package. Delivery Method will impact the project schedule market volatility can impact the Schedule.
Vital Baseline
Milestones
Drivers
Bond Schedule

## Slide 18
Good Ideas and Public Support
Public Involvement
Public Input – Public Information – Public Education
Sense of ownership
Want a voice
Financial transparency and open access
Foster community support and outreach
Lobbying Restrictions
Public Planning Session

## Slide 19
Don’t Be Afraid
Committees
Play a crucial role in the success of a project
Must have a common goal with clear and well-defined expectations
The number and types of committees vary
Committees most often result in a hierarchy based on factors such as dissemination of information, specific role in the project, approval authorities
Example: the role of a task force, advisory committee, building committee, selection committee, executive committee may all serve different functions or combined functions
Brainstorming Session

## Slide 20
Implementation Strategy
The Result of a Good Plan
01
02
03
Procurement
Critical :
Due diligence for site selection
Professional services (Geotech, survey, environmental …)
Financial and Legal advisors, staff augmentation, Mgt support
Designer and Builder
Resources
Staffing Requirements
Project Control Systems/Processes
Process Identification: identify objectives, scope, and players
Information gathering: gather process facts (who, what, when …)
Process mapping: convert into a project execution plan that supports decision making

## Slide 21
IF YOU DON’T KNOW EXACTLY WHERE YOU’RE GOING,
HOW WILL YOU KNOW WHEN YOU GET THERE?

## Slide 22
?
QUESTIONS

## Slide 23
Senior Vice President, ECM International, Inc.
Brenda Jenkins
Email
bjenkins@ecmintl.com
Address
1220 Wonder World Drive
San Marcos, TX 87662